## Executive Summary
USD Conversion to INR | 85
EXECUTIVE SUMMARY
Ownership Details |  | Project Details
Geography | APAC | Project ID
SBU |  | Project Name | Climate & Disaster Resilience
Customer | Integra | Win Classification | New Win
Customer Sub-Business |  | Billing Model
SBU Head |  | Project Type | AI ML
Account Executive (Sales) |  | Project Duration | 12 Months
Account Manager |  | Delivery Manager
Financial Summary |  | Comments
ROI Created & Included in Proposal | YES | <Use this section to share additional details about the account, strategic importance, assuptions etc.> |  | 313488
Services - Sales Price Guidance | 1487808
Services - Proposed Sales Price | 1000000
License Sales | 0
Total Sales Price | 1000000
Employee Salary Cost | 176126 | Guidance Sales Price Guidance is as per the FY23 Sales Planning Sheet. Cost is as per Finance average costs. GM Guidance is 60% Offshore FTE Revenue Guidance is $6500
Mgmt & Utilization Overheads (10%) | 0
Non-Billable Travel Cost | 0
Total Project Cost | 176126
FTE Revenue - Onsite | 0
FTE Revenue - Offshore | 4516.7118
Gross Margin% | 90%
Budget Gross Margin% | 60%
Approval Needed | YES | Reason: Approval is needed if ROI isn't created OR Sale Price/margin are below guidance
Note on E1: Input: USD->INR conversion rate, 85 (per source workbook).
Note on E13: Sales Price Guidance = Total Billing from 'Module 3 During-Disaster Integr'.
Note on E14: INPUT - Proposed Sales Price ($1,000,000). This is the cell every module's 'Budget Summary based on the Final Pricing (Cell#E14)' table references.
Note on E17: Input taken from the source workbook. Note: with a Total Project Cost of $176,126 against $1,000,000 revenue the computed GM would be 82%, not the 90% shown in E23. Reproduced exactly as photographed.
Note on E22: FTE Revenue - Offshore = Proposed Sales Price / Total FTE Man Months of Module 3 (221.4) = $4,517.
Note on E23: Hardcoded at 90% as shown in the source workbook. It does not tie to (E16-E20)/E16, which evaluates to 82%.
Note on K12: Scratch value present in the source sheet (column K); retained as-is.

## Module 1 Engineering POD
Activity / Month |  |  | Month-1 | Month-2 | Month-3 | Month-4 | Month-5 | Month-6 | Month-7 | Month-8 | Month-9 | Month-10 | Month-11 | Month-12
Consulting Phase + Data Access
Data Ingestion Methodology
Architecture Design Iterations
Pipeline & Implementation & Architecture
Architecture Hardening
QA, QC, Integration & Testing
Role / Month | Geography | ON/OFF | Month-1 | Month-2 | Month-3 | Month-4 | Month-5 | Month-6 | Month-7 | Month-8 | Month-9 | Month-10 | Month-11 | Month-12 | Total (mos) | Rate/Hr | Total Price
Account Manager | APAC | Offshore | 0.3 | 0.3 | 0.3 | [8 empty] | 0.1 | 1 | 40 | 6720
Project Manager | APAC | Offshore | 1 | 1 | 1 | 0.75 | 0.75 | 0.75 | 0.5 | 0.5 | 0.5 | 0.3 | 0.3 | 0.3 | 7.65 | 40 | 51408
Data Consultant | APAC | Offshore | [12 empty] | 0 | 40 | 0
Lead Data Consultant | APAC | Offshore | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 0.5 | 10.5 | 40 | 70560
UX Design Lead | APAC | Offshore |  |  |  | 0.75 | 1 | 1 | 1 | 0.75 | 0.5 | 0.25 |  |  | 5.25 | 40 | 35280
UX Designer | APAC | Offshore |  |  |  | 1 | 1 | 1 | 1 | 0.75 | 0.5 | 0.25 |  |  | 5.5 | 40 | 36960
Lead Data Scientist | APAC | Offshore | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.75 | 0.75 | 0.5 | 11 | 40 | 73920
Data Scientist | APAC | Offshore | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.75 | 0.5 | 0.25 | 0.25 | 9.75 | 40 | 65520
Technical Lead | APAC | Offshore | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.75 | 0.5 | 0.3 | 10.55 | 40 | 70896
Senior Developer | APAC | Offshore |  | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 0.75 | 15.75 | 40 | 105840
Developer | APAC | Offshore | [5 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 7 | 40 | 47040
QA Tester | APAC | Offshore | [8 empty] | 1 | 1 | 1 | 0.75 | 3.75 | 40 | 25200
| APAC | [13 empty] | 0 | 0 | 0
| APAC | [13 empty] | 0 | 0 | 0
Total FTE Man Months |  |  | 5.3 | 7.3 | 7.3 | 8.5 | 8.75 | 9.75 | 8.5 | 8 | 8.25 | 6.3 | 5.3 | 4.45 | 87.7 |  | 589344
*Geography is taken directly from Executive Summary sheet. Please update it in Executive Summary sheet to change Geo.
[15 empty] | Total Billing in USD |  | 589344
[15 empty] | Total Billing in INR |  | 50094240
[15 empty] | Billable Hours per Month (assumption) |  | 168
Budget Summary based on the Final Pricing (Cell#E14 in Executive Summary Tab)
Budget Parameter |  |  | Consulting | Design | Analytics | Technology | QA | Del EX
Effort (PM) |  |  | 10.5 | 10.75 | 20.75 | 17.55 | 3.75 | 7.65
Revenue (USD) |  |  | 119726.3398 | 122576.9669 | 236602.0525 | 200114.0251 | 42759.4071 | 87229.1904
Budget Break-up by Month
ON/OFF |  |  | Month-1 | Month-2 | Month-3 | Month-4 | Month-5 | Month-6 | Month-7 | Month-8 | Month-9 | Month-10 | Month-11 | Month-12 | Total | Balance
Budget |  |  | 60433.2953 | 83238.3124 | 83238.3124 | 96921.3227 | 99771.9498 | 111174.4584 | 96921.3227 | 91220.0684 | 94070.6956 | 71835.8039 | 60433.2953 | 50741.1631 | 1000000
Accrual | [14 empty] | 0 | 1000000
Invoice | [14 empty] | 0 | 1000000
Note on D35: Effort (PM) per capability is an input from the source workbook. Revenue = Effort / Total FTE Man Months (AZ26) x Proposed Sales Price ('Executive Summary'!E14).
Note on BB30: Assumption: 168 billable hours per man-month (21 days x 8 hrs). Total Price = Total (mos) x Rate/Hr x 168. This reproduces every Total Price in the source workbook exactly.

## Module 1 Cost Guidance
Module 1
| Line Item | Cost | Comments
| #FTEs | NA
| Resource Load Cost (as per resource load plan) | 589344
| SG & A, Project Risk Factors & Other Overheads etc. (25%) | 88401.6
| Total Development Cost (sales guidance) | 677745.6
| Integrated Data Engineering Module for all the 3 Hazards | 491366
| Integrated Data Engineering Module for all the 3 Hazards | 491366
| Annual Upkeep & Maintenance | 135125.65
| AWS Cloud Cost | 216000
| Final AWS Cloud Cost (rounded off for minor variations) | 216000
Final Cost Structure
| Category | Sub-Category | Year-1 | Year-2 | Year-3 | Total
| Integrated Pre-Disaster Module for all the 3 Hazards | One-time Development (professional fee) | 491366 |  |  | 491366
|  | Annual Upkeep & Maintenance | 67562.825 | 135125.65 | 135125.65 | 337814.125
|  | Total | 558928.825 | 135125.65 | 135125.65 | 135125.65
| Cloud Infrastructure Costs | AWS Costs | 216000 | 216000 | 216000 | 648000
|  | Total | 216000 | 216000 | 216000 | 648000
| TOTAL |  | 774928.825 | 351125.65 | 351125.65 | 783125.65
Note on C8: Labelled 25% in the source workbook, but the value shown is exactly 15% of the Resource Load Cost. Formula reproduces the photographed figure (=C7*0.15); the label is left as-is.
Note on C11: INPUT: one-time module price ($491,366) taken directly from the source workbook. It is not a fixed percentage of the Total Development Cost above.
Note on C13: Annual Upkeep = 27.5% of the one-time module price, derived from the photographed figures. Each module uses a different rate (M1 27.5%, M2 24%, M3 18.5%).
Note on D25: Year-1 upkeep is charged at half the annual rate (go-live part-way through year 1), per the source workbook.
Note on G26: SOURCE QUIRK, reproduced deliberately: in the original workbook this Total-column cell equals 27.5% of the one-time fee, not SUM(D26:F26). The same 27.5% is used on all three modules (it matches Module 1's upkeep rate). Correct row sum would be =SUM(D26:F26).

## Module 2 Pre-Disaster Integrate
Activity / Month |  |  | Month-1 | Month-2 | Month-3 | Month-4 | Month-5 | Month-6 | Month-7 | Month-8 | Month-9 | Month-10 | Month-11 | Month-12
Requirements and project planning
Data and methodology review
Workshops with stakeholders
Development
Integration Development (APIs)
Testing (Ground-Truth Data or On-Ground)
UAT and Go-Live
Role / Month | Geography | ON/OFF | Month-1 | Month-2 | Month-3 | Month-4 | Month-5 | Month-6 | Month-7 | Month-8 | Month-9 | Month-10 | Month-11 | Month-12 | Total (mos) | Rate/Hr | Total Price
Account Manager | APAC | Offshore | 0.5 | 0.5 | 0.5 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.1 | 0.1 | 0.2 | 0.2 | 3.1 | 40 | 20832
Project Manager | APAC | Offshore | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 12 | 40 | 80640
Data Consultant | APAC | Offshore | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 12 | 40 | 80640
Lead Data Consultant | APAC | Offshore | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 12 | 40 | 80640
UX Design Lead | APAC | Offshore |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.75 | 0.3 | 8.05 | 40 | 54096
UX Designer | APAC | Offshore |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.75 |  | 7.75 | 40 | 52080
Lead Data Scientist | APAC | Offshore | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 16 | 40 | 107520
Data Scientist | APAC | Offshore | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 24 | 40 | 161280
Technical Lead | APAC | Offshore | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 12 | 40 | 80640
Senior Developer | APAC | Offshore |  | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 16 | 40 | 107520
Developer | APAC | Offshore |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1.5 | 1.5 | 1.3 | 13.3 | 40 | 89376
QA Tester | APAC | Offshore | [6 empty] | 1 | 1 | 2 | 2 | 2 | 2 | 10 | 40 | 67200
| APAC | [13 empty] | 0 | 0 | 0
| APAC | [13 empty] | 0 | 0 | 0
Total FTE Man Months |  |  | 7.5 | 10.5 | 10.5 | 12.2 | 13.2 | 13.2 | 13.2 | 13.2 | 14.1 | 13.6 | 13.2 | 11.8 | 146.2 |  | 982464
*Geography is taken directly from Executive Summary sheet. Please update it in Executive Summary sheet to change Geo.
[15 empty] | Total Billing in USD |  | 982464
[15 empty] | Total Billing in INR |  | 83509440
[15 empty] | Billable Hours per Month (assumption) |  | 168
Budget Summary based on the Final Pricing (Cell#E14 in Executive Summary Tab)
Budget Parameter |  |  | Consulting | Design | Analytics | Technology | QA | Del EX
Effort (PM) |  |  | 24 | 15.8 | 40 | 25.3 | 10 | 12
Revenue (USD) |  |  | 164158.6867 | 108071.1354 | 273597.8112 | 173050.6156 | 68399.4528 | 82079.3434
Budget Break-up by Month
ON/OFF |  |  | Month-1 | Month-2 | Month-3 | Month-4 | Month-5 | Month-6 | Month-7 | Month-8 | Month-9 | Month-10 | Month-11 | Month-12 | Total | Balance
Budget |  |  | 51299.5896 | 71819.4254 | 71819.4254 | 83447.3324 | 90287.2777 | 90287.2777 | 90287.2777 | 90287.2777 | 96443.2285 | 93023.2558 | 90287.2777 | 80711.3543 | 1000000
Accrual | [14 empty] | 0 | 1000000
Invoice | [14 empty] | 0 | 1000000
Note on D35: Effort (PM) per capability is an input from the source workbook. Revenue = Effort / Total FTE Man Months (AZ26) x Proposed Sales Price ('Executive Summary'!E14).
Note on BB30: Assumption: 168 billable hours per man-month (21 days x 8 hrs). Total Price = Total (mos) x Rate/Hr x 168. This reproduces every Total Price in the source workbook exactly.

## Module 2 Cost Guidance
Module 2
| Line Item | Cost | Comments
| #FTEs | NA
| Resource Load Cost (as per resource load plan) | 982464
| SG & A, Project Risk Factors & Other Overheads etc. (25%) | 147369.6
| Total Development Cost (sales guidance) | 1129833.6
| Pre-Disaster Integrated POD for all the 3 Hazards | 807024
| Integrated Data Engineering Module for all the 3 Hazards | 807024
| Annual Upkeep & Maintenance | 193685.76
| AWS Cloud Cost | 353500
| Final AWS Cloud Cost (rounded off for minor variations) | 353500
Final Cost Structure
| Category | Sub-Category | Year-1 | Year-2 | Year-3 | Total
| Integrated Pre-Disaster Module for all the 3 Hazards | One-time Development (professional fee) | 807024 |  |  | 807024
|  | Annual Upkeep & Maintenance | 96842.88 | 193685.76 | 193685.76 | 484214.4
|  | Total | 903866.88 | 193685.76 | 193685.76 | 221931.6
| Cloud Infrastructure Costs | AWS Costs | 353500 | 353500 | 353500 | 1060500
|  | Total | 353500 | 353500 | 353500 | 1060500
| TOTAL |  | 1257366.88 | 547185.76 | 547185.76 | 1282431.6
Note on C8: Labelled 25% in the source workbook, but the value shown is exactly 15% of the Resource Load Cost. Formula reproduces the photographed figure (=C7*0.15); the label is left as-is.
Note on C11: INPUT: one-time module price ($807,024) taken directly from the source workbook. It is not a fixed percentage of the Total Development Cost above.
Note on C13: Annual Upkeep = 24% of the one-time module price, derived from the photographed figures. Each module uses a different rate (M1 27.5%, M2 24%, M3 18.5%).
Note on D25: Year-1 upkeep is charged at half the annual rate (go-live part-way through year 1), per the source workbook.
Note on G26: SOURCE QUIRK, reproduced deliberately: in the original workbook this Total-column cell equals 27.5% of the one-time fee, not SUM(D26:F26). The same 27.5% is used on all three modules (it matches Module 1's upkeep rate). Correct row sum would be =SUM(D26:F26).

## Module 3 During-Disaster Integr
Activity / Month |  |  | Month-1 | Month-2 | Month-3 | Month-4 | Month-5 | Month-6 | Month-7 | Month-8 | Month-9 | Month-10 | Month-11 | Month-12
Requirements and project planning
Data and methodology review
Workshops with stakeholders
Development
Integration Development (APIs)
Testing (Ground-Truth Data or On-Ground)
UAT and Go-Live
Role / Month | Geography | ON/OFF | Month-1 | Month-2 | Month-3 | Month-4 | Month-5 | Month-6 | Month-7 | Month-8 | Month-9 | Month-10 | Month-11 | Month-12 | Total (mos) | Rate/Hr | Total Price
Account Manager | APAC | Offshore | 0.5 | 0.5 | 0.5 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 3.3 | 40 | 22176
Project Manager | APAC | Offshore | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 12 | 40 | 80640
Data Consultant | APAC | Offshore | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 24 | 40 | 161280
Lead Data Consultant | APAC | Offshore | 2 | 2 | 2 | 2 | 2 | 2 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1 | 20.5 | 40 | 137760
UX Design Lead | APAC | Offshore |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.8 | 8.8 | 40 | 59136
UX Designer | APAC | Offshore |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.8 | 8.8 | 40 | 59136
Lead Data Scientist | APAC | Offshore | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 24 | 40 | 161280
Data Scientist | APAC | Offshore | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 31 | 40 | 208320
Technical Lead | APAC | Offshore | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 17 | 40 | 114240
Senior Developer | APAC | Offshore | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 20 | 40 | 134400
Developer | APAC | Offshore | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 28 | 40 | 188160
DevOps Engineer | APAC | Offshore | 1 | 1 | 1 | 1 |  |  |  |  | 1 | 1 | 1 | 1 | 8 | 40 | 53760
QA Tester | APAC | Offshore |  |  |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 16 | 40 | 107520
| APAC | [13 empty] | 0 | 0 | 0
Total FTE Man Months |  |  | 17.5 | 17.5 | 17.5 | 20.2 | 20.2 | 19.2 | 18.7 | 18.7 | 18.7 | 18.7 | 17.7 | 16.8 | 221.4 |  | 1487808
*Geography is taken directly from Executive Summary sheet. Please update it in Executive Summary sheet to change Geo.
[15 empty] | Total Billing in USD |  | 1487808
[15 empty] | Total Billing in INR |  | 126463680
[15 empty] | Billable Hours per Month (assumption) |  | 168
Budget Summary based on the Final Pricing (Cell#E14 in Executive Summary Tab)
Budget Parameter |  |  | Consulting | Design | Analytics | Technology | QA | Del EX
Effort (PM) |  |  | 44.5 | 17.6 | 55 | 45 | 16 | 12
Revenue (USD) |  |  | 200993.6766 | 79494.1283 | 248419.1509 | 203252.0325 | 72267.3893 | 54200.542
Budget Break-up by Month
ON/OFF |  |  | Month-1 | Month-2 | Month-3 | Month-4 | Month-5 | Month-6 | Month-7 | Month-8 | Month-9 | Month-10 | Month-11 | Month-12 | Total | Balance
Budget |  |  | 79042.4571 | 79042.4571 | 79042.4571 | 91237.579 | 91237.579 | 86720.8672 | 84462.5113 | 84462.5113 | 84462.5113 | 84462.5113 | 79945.7995 | 75880.7588 | 1000000
Accrual | [14 empty] | 0 | 1000000
Invoice | [14 empty] | 0 | 1000000
Note on D35: Effort (PM) per capability is an input from the source workbook. Revenue = Effort / Total FTE Man Months (AZ26) x Proposed Sales Price ('Executive Summary'!E14).
Note on BB30: Assumption: 168 billable hours per man-month (21 days x 8 hrs). Total Price = Total (mos) x Rate/Hr x 168. This reproduces every Total Price in the source workbook exactly.

## Module 3 Cost Guidance
Module 3
| Line Item | Cost | Comments
| #FTEs | NA
| Resource Load Cost (as per resource load plan) | 1487808
| SG & A, Project Risk Factors & Other Overheads etc. (25%) | 223171.2
| Total Development Cost (sales guidance) | 1710979.2
| Integrated Data Engineering Module for all the 3 Hazards | 1539881
| During-Disaster Integrated POD for all the 3 Hazards | 1539881
| Annual Upkeep & Maintenance | 284877.985
| AWS Cloud Cost | 463986
| Final AWS Cloud Cost (rounded off for minor variations) | 463986
Final Cost Structure
| Category | Sub-Category | Year-1 | Year-2 | Year-3 | Total
| Integrated Pre-Disaster Module for all the 3 Hazards | One-time Development (professional fee) | 1539881 |  |  | 1539881
|  | Annual Upkeep & Maintenance | 142438.9925 | 284877.985 | 284877.985 | 712194.9625
|  | Total | 1682319.9925 | 284877.985 | 284877.985 | 423467.275
| Cloud Infrastructure Costs | AWS Costs | 353500 | 353500 | 353500 | 1060500
|  | Total | 353500 | 353500 | 353500 | 1060500
| TOTAL |  | 2035819.9925 | 638377.985 | 638377.985 | 1483967.275
Note on C8: Labelled 25% in the source workbook, but the value shown is exactly 15% of the Resource Load Cost. Formula reproduces the photographed figure (=C7*0.15); the label is left as-is.
Note on C11: INPUT: one-time module price ($1,539,881) taken directly from the source workbook. It is not a fixed percentage of the Total Development Cost above.
Note on C13: Annual Upkeep = 18.5% of the one-time module price, derived from the photographed figures. Each module uses a different rate (M1 27.5%, M2 24%, M3 18.5%).
Note on D25: Year-1 upkeep is charged at half the annual rate (go-live part-way through year 1), per the source workbook.
Note on D27: SOURCE QUIRK, reproduced deliberately: the Final Cost Structure uses the Pre-Disaster AWS figure ($353,500), while the AWS Cloud Cost line in C16 above shows the During-Disaster figure ($463,986).
Note on G26: SOURCE QUIRK, reproduced deliberately: in the original workbook this Total-column cell equals 27.5% of the one-time fee, not SUM(D26:F26). The same 27.5% is used on all three modules (it matches Module 1's upkeep rate). Correct row sum would be =SUM(D26:F26).

## Module 3.1 During-Disaster Hyb
Activity / Month |  |  | Month-1 | Month-2 | Month-3 | Month-4 | Month-5 | Month-6 | Month-7 | Month-8 | Month-9 | Month-10 | Month-11 | Month-12
Requirements and project planning
Data and methodology review
Workshops with stakeholders
Development
Integration Development (APIs)
Testing (Ground-Truth Data or On-Ground)
UAT and Go-Live
Role / Month | Geography | ON/OFF | Month-1 | Month-2 | Month-3 | Month-4 | Month-5 | Month-6 | Month-7 | Month-8 | Month-9 | Month-10 | Month-11 | Month-12 | Total (mos) | Rate/Hr | Total Price
Account Manager | APAC | Offshore | 0.5 | 0.5 | 0.5 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 3.3 | 40 | 22176
Project Manager | APAC | Offshore | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 7 | 40 | 47040
Data Consultant | APAC | Offshore | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 12 | 40 | 80640
Lead Data Consultant | APAC | Offshore | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 12 | 40 | 80640
UX Design Lead | APAC | Offshore |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 |  |  |  | 6 | 40 | 40320
UX Designer | APAC | Offshore |  |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 9 | 40 | 60480
Lead Data Scientist | APAC | Offshore | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 24 | 40 | 161280
Data Scientist | APAC | Offshore | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 24 | 40 | 161280
Technical Lead | APAC | Offshore | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 17 | 40 | 114240
Senior Developer | APAC | Offshore | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 18 | 40 | 120960
Developer | APAC | Offshore | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 22 | 40 | 147840
DevOps Engineer | APAC | Offshore | 1 | 1 | 1 | 1 | [7 empty] | 0.5 | 4.5 | 40 | 30240
QA Tester | APAC | Offshore |  |  |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 16 | 40 | 107520
| APAC | [13 empty] | 0 | 0 | 0
Total FTE Man Months |  |  | 15.2 | 15.2 | 14.2 | 15.9 | 16.9 | 15.7 | 14.7 | 14.7 | 13.7 | 12.7 | 12.7 | 13.2 | 174.8 |  | 1174656
*Geography is taken directly from Executive Summary sheet. Please update it in Executive Summary sheet to change Geo.
[15 empty] | Total Billing in USD |  | 1174656
[15 empty] | Total Billing in INR |  | 99845760
[15 empty] | Billable Hours per Month (assumption) |  | 168
Budget Summary based on the Final Pricing (Cell#E14 in Executive Summary Tab)
Budget Parameter |  |  | Consulting | Design | Analytics | Technology | QA | Del EX
Effort (PM) |  |  | 24 | 15 | 48 | 39 | 16 | 7
Revenue (USD) |  |  | 137299.7712 | 85812.357 | 274599.5423 | 223112.1281 | 91533.1808 | 40045.7666
Budget Break-up by Month
ON/OFF |  |  | Month-1 | Month-2 | Month-3 | Month-4 | Month-5 | Month-6 | Month-7 | Month-8 | Month-9 | Month-10 | Month-11 | Month-12 | Total | Balance
Budget |  |  | 86956.5217 | 86956.5217 | 81235.6979 | 90961.0984 | 96681.9222 | 89816.9336 | 84096.1098 | 84096.1098 | 78375.286 | 72654.4622 | 72654.4622 | 75514.8741 | 1000000
Accrual | [14 empty] | 0 | 1000000
Invoice | [14 empty] | 0 | 1000000
Note on D35: Effort (PM) per capability is an input from the source workbook. Revenue = Effort / Total FTE Man Months (AZ26) x Proposed Sales Price ('Executive Summary'!E14).
Note on BB30: Assumption: 168 billable hours per man-month (21 days x 8 hrs). Total Price = Total (mos) x Rate/Hr x 168. This reproduces every Total Price in the source workbook exactly.

## Module 4 Scope Map
MODULE 4 ¦ Revised 2-Hazard Scope (Flood + Landslide) - Scope to Effort Map
Source: Straive 'Commercial Proposal: National Multi-Hazard Disaster Monitoring and Decision Support System', Revised Scope of Work. Wildfire analysis removed per client mail of 31 Jul 2026 (Ahmad Yokasano, Paques).
Sec | Scope Area | What is being built | Effort (FTE-mo) | % of Build | Value (USD)
1 | Flood Hazard Monitoring & Early Action Pipeline | WFLOW_sbm distributed hydrology; HEC-HMS urban flash; HEC-RAS 2D + LISFLOOD-FP inundation; SFINCS river-tide backwater; Siaga trigger logic; hydrograph / WSE / velocity / exposure outputs | 42 | 21.92% | 282240
2 | Landslide Hazard Monitoring & Early Warning Pipeline | SINMAP/SHALSTAB static FS; TRIGRS/Scoops3D transient pore-water; RAMMS/FLO-2D runout; 4-parameter trigger chain; susceptibility + hourly FS grids + mudflow footprint | 34 | 17.75% | 228480
3 | Integrated Analytics, Vulnerability Assessment & Network Routing | MCDM + Random Forest / Gradient Boosting vulnerability indexing; NetworkX regency graph extraction (OSM + PUPR, 50 regencies); Dijkstra / A* / RL evacuation routing | 26 | 13.57% | 174720
4 | Operational Resource & Recovery Estimation Modules | Personnel needs; relief materials; emergency fund estimation; post-disaster recovery / damage classification on satellite & drone imagery | 18 | 9.395% | 120960
5 | Architectural Data Ingestion & Dissemination Integrity | Ingestion architecture; latency SLA engineering; Pusdatinkom gateways; outbound SMS / inaRISK push; IVR voicebot + WhatsApp/Telegram feedback loop | 24 | 12.53% | 161280
6 | Hybrid Infrastructure, Deployment & SLA Hardening | On-prem BNPB DC deployment; Jakarta-region cloud burst layer; CI/CD; AES-256 / TLS 1.2+; 99.9% availability engineering | 16 | 8.351% | 107520
- | Command Centre (Pillar 1) Visualisation & UX | Read-only maps, deployment tables, cost charts, hazard overlays, UX research and design system | 14 | 7.307% | 94080
- | Programme Management, QA & UAT | Account and project management, ground-truth validation against KGE >= 0.70 and IoU >= 0.60 quality gates, UAT and go-live | 17.6 | 9.186% | 118272
Total Build Effort |  |  | 191.6 | 100% | 1287552
Note: value shown is Resource Load Cost (bill value at $40/hr x 168 hrs), before SG&A and before any discount. See 'Module 4 Cost Guidance'.
Note on E6: Effort allocation is the estimator's split of the 191.6 FTE-month resource load plan across the revised scope. It must always sum to the plan total in 'Module 4 Flood-Landslide POD'!AZ26.

## Module 4 Flood-Landslide POD
Activity / Month |  |  | Month-1 | Month-2 | Month-3 | Month-4 | Month-5 | Month-6 | Month-7 | Month-8 | Month-9 | Month-10 | Month-11 | Month-12
Requirements, Data Access & Discovery
Data Ingestion & Lakehouse Build (On-Prem)
Flood Modelling Chain Development
Landslide Modelling Chain Development
Integrated Analytics, Vulnerability & Routing
Resource/Recovery Estimation & Dissemination
Ground-Truth Validation & SLA Testing
UAT, Hybrid Deployment & Go-Live
Role / Month | Geography | ON/OFF | Month-1 | Month-2 | Month-3 | Month-4 | Month-5 | Month-6 | Month-7 | Month-8 | Month-9 | Month-10 | Month-11 | Month-12 | Total (mos) | Rate/Hr | Total Price
Account Manager | APAC | Offshore | 0.5 | 0.5 | 0.3 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 0.2 | 3.1 | 40 | 20832
Project Manager | APAC | Offshore | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 12 | 40 | 80640
Data Consultant | APAC | Offshore | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 9.5 | 40 | 63840
Lead Data Consultant | APAC | Offshore | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 12 | 40 | 80640
UX Design Lead | APAC | Offshore |  |  | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 0.5 | 0.5 |  |  | 6 | 40 | 40320
UX Designer | APAC | Offshore |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 0.5 |  | 8 | 40 | 53760
Lead Data Scientist | APAC | Offshore | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 20 | 40 | 134400
Data Scientist | APAC | Offshore | 1 | 2 | 3 | 4 | 4 | 4 | 4 | 4 | 3 | 3 | 2 | 2 | 36 | 40 | 241920
Technical Lead | APAC | Offshore | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 12 | 40 | 80640
Senior Developer | APAC | Offshore | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 21 | 40 | 141120
Developer | APAC | Offshore |  | 1 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 1 | 25 | 40 | 168000
DevOps Engineer | APAC | Offshore | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 12 | 40 | 80640
QA Tester | APAC | Offshore |  |  |  | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 15 | 40 | 100800
| APAC | [13 empty] | 0 | 0 | 0
Total FTE Man Months |  |  | 8.5 | 11.5 | 16.3 | 18.2 | 19.2 | 19.2 | 19.7 | 19.2 | 18.2 | 16.7 | 13.2 | 11.7 | 191.6 |  | 1287552
*Geography is taken directly from Executive Summary sheet. Please update it in Executive Summary sheet to change Geo.
[15 empty] | Total Billing in USD |  | 1287552
[15 empty] | Total Billing in INR |  | 109441920
[15 empty] | Billable Hours per Month (assumption) |  | 168
Budget Summary based on the Final Pricing (Cell#E14 in Executive Summary Tab)
Budget Parameter |  |  | Consulting | Design | Analytics | Technology | QA | Del EX
Effort (PM) |  |  | 24.6 | 14 | 56 | 70 | 15 | 12
Revenue (USD) |  |  | 128392.4843 | 73068.8935 | 292275.5741 | 365344.4676 | 78288.1002 | 62630.4802
Budget Break-up by Month
ON/OFF |  |  | Month-1 | Month-2 | Month-3 | Month-4 | Month-5 | Month-6 | Month-7 | Month-8 | Month-9 | Month-10 | Month-11 | Month-12 | Total | Balance
Budget |  |  | 44363.2568 | 60020.8768 | 85073.0689 | 94989.5616 | 100208.7683 | 100208.7683 | 102818.3716 | 100208.7683 | 94989.5616 | 87160.7516 | 68893.5282 | 61064.7182 | 1000000
Accrual | [14 empty] | 0 | 1000000
Invoice | [14 empty] | 0 | 1000000
Note on A18: 'Lead Data Scientist' covers the hydrology and geotechnical modelling leads (WFLOW/HEC-RAS/SFINCS and SINMAP/TRIGRS/RAMMS). 'Data Scientist' covers the flood modellers, landslide modellers and the vulnerability / damage-classification ML stream. Titles kept identical to Modules 1-3.1 so the rate card and Budget Summary logic stay consistent.
Note on D35: Capability split of the 191.6 FTE-month plan. Technology is the largest bucket because the two physics-modelling chains, dissemination layer and Command Centre are all engineering-led. Sums to AZ26.
Note on BB30: Assumption: 168 billable hours per man-month (21 days x 8 hrs), identical to Modules 1-3.1.

## Module 4 Cost Guidance
MODULE 4 ¦ Cost Guidance - Integrated Flood & Landslide (2 Hazards)
Line Item | Cost | Comments
#FTEs (peak / average) | 15.9667 | Average FTE across the 12-month build
Resource Load Cost (as per resource load plan) | 1287552 | 191.6 FTE-months @ $40/hr x 168 hrs
SG & A, Project Risk Factors & Other Overheads etc. (15%) | 193132.8 | 15% - the rate actually applied in Modules 1-3
Total Development Cost (sales guidance) | 1480684.8 | Sales-guidance price before any discount
Discount applied to reach offer price | 10% | 10% - the convention used on Module 3
Integrated Flood & Landslide Module (2 Hazards) - one-time | 1332616.32 | Bottom-up one-time professional fee
Support & Maintenance Pod (24x5 shared coverage, annual)
Role | FTE | Months | FTE-Months | Scope of cover
Support / Platform Lead | 0.25 | 12 | 3 | Single point of accountability, SLA reporting, release governance
DevOps / SRE (24x5 shared) | 0.75 | 12 | 9 | Availability >= 99.9%, latency SLA assurance, incident response, patching
Data Engineer | 0.75 | 12 | 9 | Ingestion pipeline break-fix, feed changes (BMKG / LAPAN / IoT), data quality
Data Scientist | 0.4 | 12 | 4.8 | Model drift monitoring, threshold recalibration (I-D curves, FS), seasonal retraining
Application Developer | 0.4 | 12 | 4.8 | Command Centre and dissemination-layer break-fix and minor enhancements
QA Engineer | 0.2 | 12 | 2.4 | Regression testing on releases, SLA and output quality verification
Support Pod Total | 2.75 |  | 33
S&M Resource Load Cost (annual) | 221760
SG & A and overheads (15%) | 33264
S&M sales guidance (annual) | 255024
Annual Support & Maintenance - offer price | 229521.6
Hybrid Infrastructure (annual, recurring) | 96500 | Jakarta public cloud only - on-prem BoQ excluded
Final Cost Structure (bottom-up)
Category | Sub-Category | Year-1 | Year-2 | Year-3 | Total
Integrated Flood & Landslide Module (2 Hazards) | One-time Development (professional fee) | 1332616.32 |  |  | 1332616.32
| Annual Support & Maintenance |  | 229521.6 | 229521.6 | 459043.2
| Total | 1332616.32 | 229521.6 | 229521.6 | 1791659.52
Hybrid Infrastructure Costs | Hybrid Infrastructure (recurring) | 96500 | 96500 | 96500 | 289500
| Total | 96500 | 96500 | 96500 | 289500
TOTAL |  | 1429116.32 | 326021.6 | 326021.6 | 2081159.52
Note on C24: Year 1 S&M is nil: hypercare and warranty sit inside the one-time build fee, matching Section 7 of the proposal where Year 1 S&M shows a dash.

## Module 4 Hybrid Infra
MODULE 4 ¦ Hybrid Infrastructure Estimate (Annual, Recurring)
Section 6 of the revised proposal moves the deployment from pure AWS to a Hybrid-Cloud architecture: on-premise BNPB Data Centre plus a Jakarta-region public cloud burst layer. Only the cloud layer sits in Straive's recurring price.
A. Jakarta-Region Public Cloud - IN Straive recurring price
Layer | Component | Deployment | Purpose | Annual Cost (USD)
Compute | Elastic GPU compute (AI/ML training & burst inference) | Jakarta Public Cloud | Seasonal burst capacity during peak hazard events | 26000
Compute | Managed Kubernetes / container orchestration | Jakarta Public Cloud | Burst inference and modelling-chain orchestration | 11000
Storage | Object storage extension & archive tier | Jakarta Public Cloud | Overflow beyond on-prem 241 TB, long-term hazard archive | 13500
Data | Geospatial data egress & processing | Jakarta Public Cloud | Sentinel-1 SAR, GLO-30/FABDEM, WorldPop, OSM pulls | 9000
Streaming | Streaming & IoT telemetry ingest | Jakarta Public Cloud | Peak-event sensor, radar and rain-gauge throughput | 7500
DevOps | Monitoring, logging and tracing | Jakarta Public Cloud | Assurance of <= 20 min end-to-end EAS latency SLA | 6000
Security | Secrets manager / KMS / security tooling | Jakarta Public Cloud | AES-256 at rest, TLS 1.2+ in transit, key custody | 4500
Networking | API gateway, load balancer and CDN | Jakarta Public Cloud | Dissemination APIs, webhooks, Command Centre delivery | 7000
Resilience | Backup and DR replication | Jakarta Public Cloud | Off-site replication of on-prem data lake | 6500
Networking | On-prem to cloud interconnect | Hybrid | Dedicated link between BNPB DC and Jakarta region | 5500
Total Hybrid Infrastructure (Annual, Recurring) |  |  |  | 96500
B. On-Premise BNPB Data Centre - EXCLUDED, client-supplied (BoQ reference)
| Module / Component | Specification & Quantity Details |  | Straive Cost
| Ingestion | 5 servers sized to handle ~1.7 TB/day |  | 0
| Storage | ~241 TB NAS/SAN with 90-day retention and 30% buffer |  | 0
| ETL / Data Engineering | 4 Spark/Airflow servers |  | 0
| AI/ML Inference | 2 GPU servers (NVIDIA T4 or A2) for low-latency predictions |  | 0
| Data Centre Facilities | Rack space, power, cooling, LAN/WAN, physical security |  | 0
Total On-Premise in Straive price (hardware supplied by client) |  |  |  | 0
C. Explicit Exclusions - must appear in the commercial
1 | On-premise hardware procurement, installation and setup - performed by the client's infrastructure partner (Paques Team) per Section 8 Technical & Operational Assumptions.
2 | SMS, IVR and OTT broadcast carrier charges for the 170-180 million active number population - borne by BNPB / Pusdatinkom and the participating Telcos.
3 | Third-party commercial data licences (commercial satellite tasking, proprietary basemaps, paid weather feeds).
4 | BNPB data centre facilities, power, cooling and physical security.
5 | Any features outside the defined scope - chargeable on a Time & Material basis.
Note on C21: COMMERCIAL RISK: the BoQ table sits directly above the 'IT Infrastructure' line in Section 7 of the proposal. Unless exclusion is stated on the same page, BNPB will read the recurring infrastructure fee as covering these servers. Section 8 assigns hardware setup to the Paques Team but never says the hardware itself is out of Straive's price.
Note on F7: Line-item cloud costs are the estimator's sizing for a Jakarta-region burst layer supporting two hazard pipelines. They are inputs, not quotes - confirm against a live cloud calculator before the price is committed.

## Module 4 Commercial Recon
MODULE 4 ¦ Bottom-Up Estimate vs Published Option 2 Commercial
Published figures are taken from Section 7 'Commercial Terms' of the Straive proposal (Option 2 - 2 Hazards led by Straive: Flood & Landslide). Bottom-up figures are built from the Module 4 resource load plan and hybrid infra sheet.
Commercial Line | Bottom-Up (this workbook) | Published Option 2 | Variance (USD) | Variance % | Read-out
AI Solution Development + Data Engineering (one-time) | 1332616.32 | 1176597 | 156019.32 | 13.26% | Published price is under the bottom-up build by ~13%. Either descope, or book the difference as a deliberate strategic discount.
IT Infrastructure (annual, recurring) | 96500 | 91974 | 4526 | 4.921% | Broadly aligned. Confirm the cloud sizing against a live calculator.
Support & Maintenance (annual, recurring) | 229521.6 | 199795 | 29726.6 | 14.88% | Published S&M funds ~2.4 shared FTE against a 2.75 FTE pod for a 99.9% / 24x5 commitment. Thinnest line in the deal.
Year-wise position
Year 1 (build + infra) | 1429116.32 | 1268571 | 160545.32 | 12.66%
Year 2 (infra + S&M) | 326021.6 | 291769 | 34252.6 | 11.74%
Year 3 (infra + S&M) | 326021.6 | 291769 | 34252.6 | 11.74%
3-Year Total Contract Value | 2081159.52 | 1852109 | 229050.52 | 12.37%
Discount position against sales guidance
Total Development Cost (sales guidance) | 1480684.8 |  | Full guidance price before discount
Bottom-up offer price (10% discount) | 1332616.32 | 10% | The Module 3 convention
Published Option 2 price | 1176597 | 20.54% | Embeds roughly twice the intended discount
Additional discount embedded in published price | 156019.32 | 10.54% | Approve this explicitly, or recover it via scope
Levers to close the gap
1 | Hold the published price and book the delta as an approved strategic discount - this is a New Win and the Executive Summary already flags Approval Needed = YES.
2 | Reduce Year-1 build scope: Section 4 (Resource & Recovery Estimation, 18.0 FTE-months) is the most severable block and is not part of the Early Action critical path.
3 | Move the citizen feedback loop (IVR voicebot, WhatsApp/Telegram) in Section 5.2 to a Phase 2 change request on T&M.
4 | Re-price S&M at the published number but cut the commitment to 12x5 with an on-call rota, rather than 24x5 against a 99.9% SLA.
5 | Confirm on-prem BoQ hardware exclusion in writing before signature - if it lands in Straive scope the gap widens materially.
Note on D6: INPUT - published Option 2 pricing, Section 7 Commercial Terms of the Straive revised proposal. Update here if the offer price is renegotiated.

## Cloud Infra Estimate
AWS Resource Estimate
Service Category | Service Type | Region | Description | Estimated Annual Cost for Engineering POD (USD) | Estimated Annual Cost for Pre-Disaster Integrated POD (USD) | Estimated Annual Cost for During-Disaster Integrated POD (USD)
Web | Amazon CloudSearch or OpenSearch | Asia Pacific (Jakarta) | Search interface for hazard metadata, incidents, historical events | 18000 | 22000 | 24000
Compute | Amazon EKS (Kubernetes Service) | Asia Pacific (Jakarta) | Container orchestration for ML services and real-time APIs | 32000 | 40000 | 50000
DevOps | Amazon CloudWatch + X-Ray | Asia Pacific (Jakarta) | Monitoring, logging, and tracing across services | 15000 | 10000 | 20000
Security | AWS Secrets Manager / KMS | Asia Pacific (Jakarta) | Securing credentials, API keys, model secrets | 10000 | 7000 | 10000
Developer Tools | AWS AppConfig + CodePipeline | Asia Pacific (Jakarta) | Manage app configurations, model toggles, feature flags | 8000 | 10000 | 12000
Networking | AWS Application Load Balancer (ALB) | Asia Pacific (Jakarta) | Routing real-time traffic for disaster alert APIs | 10000 | 12000 | 16000
Compute | Auto Scaling with EC2 Spot Instances | Asia Pacific (Jakarta) | Scale compute for training/inference workloads | 35000 | 46000 | 56000
AI | Amazon SageMaker (Core ML) | Asia Pacific (Jakarta) | Model training & inference for hazard prediction | 28000 | 48000 | 70000
AI | SageMaker Geospatial Capabilities | Asia Pacific (Jakarta) | Analyze satellite imagery and geospatial risk for flood/fire/landslide | 30000 | 70000 | 85000
AI | AWS IoT + Kinesis (Real-time Feeds) | Asia Pacific (Jakarta) | Ingest and process sensor/weather feeds for live alerts | 15000 | 55000 | 85000
Front-End | AWS Amplify + MapLibre/Mapbox GL JS | Asia Pacific (Jakarta) | Dashboard with satellite map overlays, historical and live hazard visualizations | 15000 | 33500 | 35986
Total Cost Estimates |  |  |  | 216000 | 353500 | 463986
Note on E4: All per-service annual costs are inputs quoted from the source workbook (AWS Asia Pacific / Jakarta region pricing).

## Assumptions
Assumptions
This estimate is based on the assumptions that roughly data processing is involved daily consisting of the following type of data sources. Only relevant data sources for each use case will be considered. Additional Data sources aren't included as part of this estimate.
Includes either fully on-prem, cloud or hybrid deployments as needed by the client or partner
Any Change Requests to the solution features will be charged on a T&M (Time & Material) basis
Solution Development - Includes model dev, integration dev and support to set up the solution within client infrastructure
Support & Maintenance : 24X5 with shared staffed coverage. Includes the upkeep, break-fix of the data engineering modules along with SLA adherence and performance optimization of the system
SLAs have been discussed in detail in the appropriate section of this proposal. Slide Name - SLAs, RACI Matrix – Support & Maintenance Overview
**IT Infrastructure includes solution hosting, storage, environments, database, networking, compute, security for the Data Management Module ONLY